STRATEGIC PLANNING DOCUMENT

90-DAY BUSINESS PLAN

& MARKETING / GO-TO-MARKET STRATEGY

Z-GATE LTD  ·  Where Business Meets Technology

| Scope | Kigali launch (Nyarugenge, Gasabo, Kicukiro) → countryside phase 2 |
| --- | --- |
| Horizon | First 90 days from registration, 19 August 2026 |
| Divisions | Advisory · Academy · Tech · Data |
| Prepared By | Z-GATE Business Project Development Desk |
| Date Issued | 25 August 2026 |

PART A Full Business Plan — First 90 Days

— A1 — EXECUTIVE SUMMARY

# Executive Summary

Z-GATE LTD enters the market with its main registered activity already licensed — advisory and representation before tax authorities — and three complementary divisions (Academy, Tech, Data) ready to be sequenced behind it. The first 90 days are built around one insight from the research: Rwandan SMEs are formally required to use Electronic Billing Machines for every sale, yet 59% report difficulty operating them and 51% cite affordability as a barrier. That gap is Z-GATE Advisory's flagship entry point, and it opens the door for Academy, Tech, and Data to follow inside the same client relationship.

Target by Day 90: Advisory carrying 10 retainer clients, Academy running its first two cohorts, Tech and Data live with internal reference builds and first external clients in progress. Everything below is sequenced to reach that point without overextending a single-founder company with no recorded employees at registration.

— A2 — MARKET CONTEXT

# Market Context & Research Findings

Rwanda's MSME sector accounts for 98% of all registered businesses, employs over 2.5 million people, and contributes roughly a third of national GDP — the addressable market for a compliance-and-systems company is broad and structurally central to the economy. RDB's 2025 Annual Report recorded USD 2.62 billion in registered investment across 799 projects, up from 612 in 2024, with continued digitization of the One Stop Centre's 400+ services.

## Kigali, in numbers

| Metric | Figure |
| --- | --- |
| Kigali population (2026 est.) | ≈ 2.07 million |
| Internet users, Rwanda (end 2025) | 5.01M (34.2% penetration) |
| Mobile connections, Rwanda | 13.0M (88.7% of population) |
| SMEs reporting difficulty operating EBM | 59% |
| SMEs citing EBM affordability concerns | 51% |
| Commercial buildings by district (sample) | Gasabo 55.9% · Nyarugenge 37.1% · Kicukiro 7.0% |

Sources: RDB 2025 Annual Report; Ministry of Trade & Industry; DataReportal Digital 2026 Rwanda; peer-reviewed EBM/VAT compliance studies (Rwanda SMEs); IGC Kigali commercial real estate study.

— A3 — TARGET SEGMENTS

# Target Customer Segments

| Segment | Where | Core Need | Division |
| --- | --- | --- | --- |
| Formal micro & small traders | Nyarugenge CBD, Kimironko | EBM operation, VAT filing, bookkeeping | Advisory |
| Mid-size firms & corporates | Kacyiru, Kimihurura, Remera (Gasabo) | Bundled advisory + systems, outsourced reporting | Advisory + Tech + Data |
| Youth & career-changers (18–24, largest online demo) | Kigali-wide, Facebook/Instagram-heavy | Job-ready computer & data skills | Academy |
| NGOs & SMEs with manual records | Kigali-wide | Data entry, processing, reporting | Data |

— A4 — COMPETITIVE LANDSCAPE

# Competitive Landscape

| Player | Serves | Price Tier | Strength | Gap Z-GATE Fills |
| --- | --- | --- | --- | --- |
| Big 4 (PwC, KPMG East Africa) | Large corporates, multinationals | High | Global standard, brand trust | Priced out of SME market; no training/data bundle |
| Mid-market firms (HLB MN, NSP Associates, RUMA CPA) | SMEs & mid-size companies | Medium | Local depth, RRA relationships | Advisory-only; no Tech/Academy/Data bundle |
| ALSM Consulting Group | SMEs to multinationals; Rwanda/Uganda/India/UAE | Medium–High | 55 staff, 350+ clients, bundles advisory with Zoho/Frappe tech implementation | Closest direct competitor — proof the bundled model works |
| Training providers (kLab, Andela ATLP, Zeisnet, Sokrab) | Youth, corporates | Low–Medium | Established training brands, some free | Training-only; no compliance or data services attached |

Z-GATE's positioning: mid-market pricing, Big-4-adjacent discipline, and the one bundle — compliance, skills, systems, data — that no single competitor currently offers together in one retainer.

— A5 & A6 — ROADMAP

# 90-Day Roadmap by Division

| Division | Month 1 | Month 2 | Month 3 (Day 90 target) |
| --- | --- | --- | --- |
| Advisory | Launch EBM/VAT compliance service; onboard first 3–5 retainer clients in Nyarugenge CBD | Expand to Gasabo corporates; formalize bookkeeping packages | 10 active retainer clients; compliance calendar productized |
| Academy | Design first 2 courses from Advisory's own expertise (tax basics, EBM operation) | Run first cohort (target 15–20 learners); collect testimonials | Second cohort launched; 30+ trained cumulative |
| Tech | Scope and start Advisory's internal client portal | Ship portal MVP; begin Data's reporting pipeline | Internal tools live; first external Tech conversation opened |
| Data | Define standard reporting templates using Advisory's own client data | Pilot BI dashboard internally | First external Data client onboarded |

— A7 — STAFFING PLAN

# Staffing & Organization (First 90 Days)

The registration certificate records no employees as of the registration date — every division currently runs through the founder. Hiring should follow revenue, not precede it, and should prioritize the flagship division first.

- Month 1: one Advisory associate/bookkeeper (full- or part-time) to free the founder for sales and Tech oversight; a part-time marketing coordinator to run the launch calendar.

- Month 2: one contract Academy trainer/facilitator (drawn from Rwanda's active trainer pool — kLab, Andela, university lecturers) to run the first cohort without pulling the founder off Advisory.

- Month 3: one junior developer (Tech, contract or intern) and one data analyst (Data), both scoped initially against internal tools before external client work.

— A8 — BUDGET SNAPSHOT

# 90-Day Budget Allocation

Z-GATE LTD is capitalized at RWF 5,000,000 in ordinary share capital. The allocation below is drawn directly from the role-by-role 90-Day Financial Model (Revenue & Cost Model sheet) rather than an independent estimate, so the two documents agree.

| Category | 90-Day Amount | Share |
| --- | --- | --- |
| Marketing & brand launch | RWF 1,250,000 | 25% |
| Staffing & contractors | RWF 2,200,000 | 44% |
| Tools & software (accounting, EBM-compliant systems, LMS, hosting) | RWF 1,000,000 | 20% |
| Legal, compliance & activity-code review | RWF 500,000 | 10% |
| Total committed 90-day spend | RWF 4,950,000 | 99%* |

*Rounding. A RWF 500,000 contingency reserve is tracked separately in the Financial Model — held, not drawn in the base case, and funded from incoming revenue rather than carved out of the starting capital up front. Revenue of RWF 4,620,000 over the same 90 days leaves Z-GATE with a closing cash balance of RWF 4,670,000 (93% of starting capital retained) — see the Financial Model's Cash Flow and Summary Dashboard sheets for the month-by-month build-up.

— A9 — RISK REGISTER

# Risk Register & Mitigation

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Single-founder dependency across all 4 divisions | High | Hire Advisory associate in Month 1; document processes as they're built |
| Cash flow gap before first invoices are collected | Medium | Prioritize Advisory retainers (fastest to revenue); keep Month 1 spend lean |
| 5 REVIEW-status activity codes create brand/legal ambiguity | Medium | Resolve with legal counsel before heavy marketing spend (see Section A2 in prior report) |
| Established bundled competitor (ALSM) already in market | Medium | Differentiate on Academy + Data, which ALSM does not offer |
| EBM/tech vendor dependency for compliance tooling | Low | Maintain relationships with 2+ certified EBM software providers |

— A10 — DAY-90 KPIS

# Success Metrics at Day 90

- Advisory: 10 active retainer clients; compliance calendar service productized and repeatable.

- Academy: 2 cohorts run, 30+ learners trained cumulative, first testimonials collected.

- Tech: internal client portal and reporting pipeline live; at least 1 external Tech conversation in progress.

- Data: 1 external Data client onboarded on the standard reporting template.

- Marketing: qualified lead pipeline of 500+ contacts across Facebook, LinkedIn and WhatsApp Business channels (see Part B).

PART B Marketing & Go-to-Market Strategy

— B1 — POSITIONING

# Brand Positioning & Message House

Primary message: stop juggling four vendors for compliance, skills, systems and data — Z-GATE is the one gate for all four. Every campaign in the first 90 days should trace back to this single line; division-specific messages are supporting pillars, not replacements for it.

| Compliance certainty | Practical skills | Systems that work | Numbers you can trust |
| --- | --- | --- | --- |

— B2 — PERSONAS

# Target Audience Personas

| Solange — CBD Shop Owner |
| --- |
| Where | Nyarugenge CBD / Kimironko |
| Primary channel | WhatsApp Business, word of mouth |
| Core pain | Struggles operating her EBM; unsure if she owes VAT this quarter |

| Eric — Operations Manager |
| --- |
| Where | Kacyiru / Kimihurura / Remera (Gasabo) |
| Primary channel | LinkedIn, referrals |
| Core pain | Juggling separate vendors for books, systems, and reporting |

| Aline — Recent Graduate |
| --- |
| Where | Kigali-wide |
| Primary channel | Facebook, Instagram |
| Core pain | Needs a job-ready certificate employers actually recognize |

| Jean — Cooperative Lead |
| --- |
| Where | Huye / Musanze (Phase 2) |
| Primary channel | Phone calls, local associations |
| Core pain | No digital records; trusts people over ads |

— B3 — CHANNEL STRATEGY

# Channel Strategy for Kigali

| Channel | Why (Research Basis) | Primary Use |
| --- | --- | --- |
| Facebook | 1.78M users in Rwanda (12% of population), dominant marketing platform, 18–24 largest segment | Awareness content, EBM-education video series, Academy course promotion |
| LinkedIn | 570–584K members (3.9% of pop.); ads reach 6.9% of adults 18+ | B2B outreach to Gasabo corporates, Tech/Data case studies, hiring |
| WhatsApp Business | 13M mobile connections (88.7% of pop.) — near-universal reach | Direct SME sales conversations, appointment booking, receipts |
| In-person / partnerships | PSF district chapters, RDB One Stop Centre, ICPAR | Trust-building, referral pipeline, credibility for Advisory |

— B4 — CAMPAIGN CALENDAR

# 90-Day Content & Campaign Calendar

| Phase | Focus |
| --- | --- |
| Month 1 — Awareness | Brand launch across Facebook/LinkedIn; EBM-compliance educational content series; introductory meetings with PSF chapters and RDB referral contacts |
| Month 2 — Lead Generation | Free EBM compliance clinic (in-person, Nyarugenge); Academy taster session; targeted LinkedIn outreach to Gasabo operations managers |
| Month 3 — Conversion & Proof | Publish first client case studies; launch referral incentive for existing Advisory clients; scouting visit to Huye and Musanze for Phase 2 |

— B5 — KIGALI ROLLOUT

# Kigali District Rollout Sequence

- 1st — Nyarugenge (CBD): historic financial district, ~37% of Kigali's commercial buildings, closest to RRA/RDB offices. Advisory anchor launches here.

- 2nd — Gasabo (Kacyiru, Kimihurura, Remera): largest commercial concentration (55.9% of sampled buildings), home to corporates and diplomatic/government offices. Tech and Data follow Advisory in here.

- 3rd — Kicukiro: residential, transit and industrial zones, including the airport corridor. Strongest fit for Data's entry/processing services and logistics-sector clients.

— B6 — COUNTRYSIDE GROWTH STRATEGY

# Countryside Expansion Strategy (Phase 2, Month 4+)

Rwanda's National Strategy for Transformation designates six secondary cities — Huye, Muhanga, Musanze, Nyagatare, Rubavu, Rusizi — as growth poles to relieve pressure on Kigali, backed by ongoing road and infrastructure investment (RUDP II). Urban population in these cities is growing roughly 3.2% per year. Two are the strongest first targets:

- Huye — the Southern corridor city along Highway 1 via Muhanga, known as Rwanda's intellectual and cultural centre and a human-capital hub. Strong fit for Academy first: training travels cheaply and builds trust ahead of a compliance sale.

- Musanze — the Virunga-belt city with a growing tourism and agriculture-driven commercial base. Good second target once the Huye playbook is proven.

Recommended sequencing: Academy roadshow first (lowest cost, highest trust, no local office required), Advisory delivered hybrid/remote once trust is established, Tech and Data remain Kigali-hub with remote delivery — internet reliability and developer/analyst talent are still concentrated in Kigali per the research above.

— B7 — PARTNERSHIPS

# Partnerships & Referral Network

| Partner | Value to Z-GATE |
| --- | --- |
| RDB One Stop Centre | Referral pipeline for newly registered businesses needing Advisory |
| PSF (Private Sector Federation) district chapters | Trust-building, SME access in Nyarugenge and secondary cities |
| ICPAR (Institute of Certified Public Accountants Rwanda) | Professional credibility for Advisory |
| Universities & TVET schools (Academy trainer pipeline) | Contract trainers and course credibility |
| Software vendors (Zoho / Frappe or equivalent) | Implementation partnership for Tech, following the model ALSM already validated |

— B8 & B9 — BUDGET & MEASUREMENT

# Marketing Budget & KPIs

Recommend testing paid digital spend at a modest scale in Month 1 (Rwanda's total social ad market is projected around USD 15M for 2026 — a new entrant should test small and scale what converts) alongside low-cost, partnership-led tactics (PSF introductions, RDB referrals) that carry no media cost.

- Reach: combined Facebook + LinkedIn reach of 15,000+ unique accounts by Day 90.

- Leads: 500+ qualified contacts captured across WhatsApp Business, Facebook, and LinkedIn.

- Conversion: 10 Advisory retainer clients, 30+ Academy learners, 1 Data client, 1 Tech external conversation (mirrors Part A KPIs).

- Partnership pipeline: active referral relationship with at least 1 PSF chapter and the RDB One Stop Centre by Day 90.

— RECOMMENDATIONS

# Strategic Recommendations

- Lead with the EBM/VAT compliance pain point as Advisory's flagship hook — it is the most documented, most acute problem in the research (59% of SMEs struggle to operate EBM; 51% cite affordability).

- Resolve the five REVIEW-status registered activity codes (photojournalism, materials testing, architecture, print publishing, inpatient consulting) with legal counsel before scaling marketing spend, so the public registration record matches the brand the market will see.

- Hire the first Advisory associate before the first marketing hire — Advisory is both the flagship and the current single-founder bottleneck.

- Build Tech and Data first as internal reference tools (Advisory's own portal, Advisory's own reporting) before selling either division externally — a working internal case study sells faster and costs less than a campaign.

- Stay Kigali-only for the first 90 days; open Phase 2 in Huye and Musanze in Month 4+, leading with Academy, which travels cheapest and builds trust fastest.

- Track ALSM Consulting Group as the closest direct competitor — its bundled advisory-plus-technology model is existing proof that the Rwandan market rewards integration over single-service providers.

This plan and strategy are grounded in the market research summarized in Part A, Section A2, and should be revisited at Day 90 against the KPIs in Sections A10 and B9 before committing to Phase 2 countryside expansion.