BUSINESS PROJECT DEVELOPMENT REPORT

Z-GATE LTD

Where Business Meets Technology

| Company Code / TIN | 156848508 |
| --- | --- |
| Registration Date | 19 August 2026 |
| Category / Type | Private — Company Limited by Shares |
| Registered Office | Inyarurembo, Kiyovu, Nyarugenge, Kigali, Rwanda |
| Prepared For | Aime Serge UKOBIZABA — Managing Director |
| Prepared By | Z-GATE Business Project Development Desk |
| Date Issued | 24 August 2026 |

— SECTION 01

# Company Registration Summary

Source: Office of the Registrar General (RDB), Full Registration Information of Domestic Company, printed 19 August 2026. This section restates the certificate's core facts as the factual foundation for the strategy that follows.

| Company Name | Z-GATE LTD |
| --- | --- |
| Managing Director | Aime Serge UKOBIZABA (also Chairperson, Board) |
| Phone / Email | +250 792 957 513 · info@zgaterw.com |
| Financial Year Start | 1 January |
| Founding Shareholder | Aime Serge UKOBIZABA — 100 Ordinary Shares (100%) |

## Share Capital Structure

| Share Group | Value / Share (RWF) | Shares Issued | Share Capital (RWF) |
| --- | --- | --- | --- |
| Ordinary Share | 50,000 | 100 | 5,000,000 |

Total unissued shares: 0. The company is fully subscribed by its founding shareholder at incorporation — a clean base for a future co-founder, employee equity pool, or investor round without needing to unwind an existing cap table.

— SECTION 02

# Strategic Business Activity Portfolio

Z-GATE LTD is registered under 21 business-activity codes (1 main + 20 other), which is typical of an RDB One Stop Centre registration covering present and possible future activity. A strategy project's first job is to sort these into what the company should actually run on, what to hold in reserve, and what no longer serves the brand. The table below maps every registered code to the Z-GATE division it belongs to and recommends a strategic status.

| Code | Registered Activity | Division | Status |
| --- | --- | --- | --- |
| SM692005 | Advisory activities & representation before tax authorities | Advisory | CORE — flagship |
| SM692004 | Preparation of personal & business income tax returns | Advisory | CORE |
| SM692001 | Recording of commercial transactions (bookkeeping) | Advisory | CORE |
| SM702001 | Business & management advisory / operational assistance | Advisory | CORE |
| SM749011 | Other technical consulting | Advisory | CORE |
| SJ620101 | Software, systems, app & web design and coding | Tech | CORE — flagship |
| SJ620202 | Onsite management of client computer systems & data facilities | Tech | CORE |
| SJ582001 | Publishing of readymade software (OS, apps, games) | Tech | ADJACENT |
| SJ631201 | Search-engine-driven web directory / database hosting | Tech | ADJACENT |
| SJ631101 | Infrastructure provision for hosting data processing | Tech / Data | ADJACENT |
| SJ631106 | Data entry services | Data | CORE |
| SJ631105 | Data processing activities | Data | CORE — flagship |
| SP854914 | Computer training | Academy | CORE — flagship |
| SP852205 | Computer repair training | Academy | ADJACENT |
| SN783001 | Provision of human resources for client businesses | New line | ADJACENT |
| SJ611002 | Purchase/resale of network capacity & telecom services | Tech | RESERVE |
| SM742003 | Activities of photojournalists | Unrelated | REVIEW |
| SM712001 | Physical / chemical / analytical testing of materials | Unrelated | REVIEW |
| SM711001 | Architectural consulting (design, planning, landscape) | Unrelated | REVIEW |
| SJ581901 | Publishing of catalogs, photos, prints, advertising material | Unrelated | REVIEW |
| SQ862006 | Private consultants' services to inpatients | Unrelated | REVIEW |

## Reading the Portfolio

- CORE (green) — 11 activities already align directly with the four Z-GATE divisions and should carry the brand, marketing spend, and delivery standards built in the identity guide.

- ADJACENT (amber) — 5 activities are legitimate near-term growth lines (software publishing, hosting infrastructure, HR provision, computer repair training) worth a 6–12 month feasibility review before active investment.

- REVIEW (red) — 5 activities (photojournalism, materials testing, architectural consulting, print publishing, inpatient consulting services) fall well outside the Advisory / Academy / Tech / Data model. Recommend confirming with legal counsel whether these were selected in error during One Stop Centre registration; if not needed, they can be removed via an RDB company-details update to keep the public registration record aligned with the brand.

- N/A — Provision of human resources for client businesses (SN783001) doesn't fit an existing division. It's a natural fifth line — 'Z-GATE People' — if the company wants to pursue staffing/outsourcing; otherwise recommend holding it in reserve.

— SECTION 03

# Four-Division Operating Model

The eleven CORE activities resolve cleanly into the four-division model already established in the Z-GATE brand identity. This is the operating structure the business plan, marketing plan, and hiring plan should be built around.

Z-GATE ADVISORY

Tax & Business Consulting

Registered codes in production: SM692005, SM692004, SM692001, SM702001, SM749011

Advisory is the anchor division and the company's registered main business activity. It should be first to launch, first to bill, and the reference point for how every other division is expected to perform: precise, licensed, and directly accountable to a tax authority deadline.

Z-GATE ACADEMY

Professional Training

Registered codes in production: SP854914, SP852205

Academy currently covers computer training and computer repair training. Near-term opportunity: package Advisory's own tax and bookkeeping expertise into a short course — the division can be seeded with content the company already owns.

Z-GATE TECH

Technology Solutions

Registered codes in production: SJ620101, SJ620202, SJ582001, SJ631201, SJ631101

Tech covers software/web development and onsite systems management, with software publishing and hosting infrastructure as adjacent extensions. Recommend Tech's first roadmap be internal: build Advisory's own client portal and Data's own reporting pipeline before selling externally — a working reference case sells faster than a slide deck.

Z-GATE DATA

Data Analytics & Business Intelligence

Registered codes in production: SJ631106, SJ631105

Data covers data entry and data processing today. Its highest-value near-term move is to formalize an analytics/BI layer on top of raw processing — most of the analytical tooling can be built by Z-GATE Tech, making Data the first proof that the four divisions compound each other.

— SECTION 04

# SWOT Analysis

| STRENGTHS - Licensed tax-representation activity already registered — legal foundation for Advisory is in place from day one. - Four divisions are complementary, not competing — each can be a paying reference client for the others. - Clean cap table (100% founder-held, 0 unissued shares) gives flexibility for a future raise or equity hire. | WEAKNESSES - No employees recorded on registration date — every division currently depends on the same founder. - Registration spans 21 activity codes, which dilutes brand focus and market positioning if left unmanaged. - Academy and Data are the least developed divisions relative to Advisory and Tech. |
| --- | --- |
| OPPORTUNITIES - Bundle four services one client already needs (compliance, training, systems, reporting) into a single retainer. - Rwanda's mandatory EBM invoicing and VAT thresholds create a recurring compliance-tooling need Tech + Advisory can jointly own. - Academy courses built from Advisory's own expertise are near-zero-cost to produce. | THREATS - Five REVIEW-status activities (healthcare consulting, architecture, materials testing, etc.) create legal and reputational ambiguity if left registered without intent. - Single-founder dependency is a continuity risk for clients signing multi-year advisory contracts. - Standalone competitors exist in each of the four categories individually — differentiation depends on the bundle, not any one service. |

— SECTION 05

# Cross-Departmental Development Plan

A well-developed business project is not one department's plan — it is six functions moving in the same 90-day window. Each row below is a workstream owner, its immediate objective, and the milestone that proves it's done.

| Function | Objective (First 90 Days) | Milestone |
| --- | --- | --- |
| Marketing & Brand | Launch the Z-GATE identity system across web, social and print; produce one case study per division within 90 days. | Brand guide rollout, website, first client testimonial |
| Finance & Advisory Operations | Stand up Advisory as the revenue anchor; build the filing/compliance calendar into a client-facing service. | First 10 Advisory retainer clients, compliance calendar live |
| Technology & Product | Ship Advisory's client portal and Data's reporting pipeline as the first internal Tech deliverables. | Client portal MVP, internal reporting pipeline |
| People & Learning (Academy) | Convert Advisory's in-house expertise into the first two Academy courses; hire or contract first trainer. | 2 courses live, first cohort enrolled |
| Data & Analytics | Formalize a BI layer on top of existing data processing/entry services; define standard reporting templates. | Standard BI dashboard template, first Data client |
| Legal & Regulatory Compliance | Review the 5 REVIEW-status activity codes with legal counsel; file any RDB company-detail updates needed. | Activity code review complete, BO filings current |

— SECTION 06

# Regulatory Compliance Calendar

Drawn from the compliance obligations printed on the back of the RDB registration certificate. This is the calendar Advisory should manage first — for itself, before offering it as a client service.

| Obligation | Timing / Trigger | Frequency |
| --- | --- | --- |
| Annual Income Tax return | January – March (following year) | Annual |
| Quarterly Income Tax prepayments | By 30 Jun, 30 Sep, 31 Dec | Quarterly |
| Annual company returns & accounts (private co.) | January – July (following year) | Annual |
| PAYE registration & payment | Ongoing — if any employee earns > RWF 60,000 basic salary | Ongoing |
| VAT registration | Mandatory above RWF 5M/quarter or RWF 20M/year turnover | Threshold-triggered |
| EBM (Electronic Billing Machine) invoicing | Required from registration — all sales | Ongoing |
| Beneficial Owner (BO) information update | Within 14 days of any change | As needed |
| Company detail changes (name, address, capital, etc.) | Report to Registrar General via RDB portal | As needed |

This report summarizes the obligations as printed on the certificate for planning purposes only; it is not tax or legal advice. Confirm current deadlines and thresholds directly with RRA / RDB before filing.

— SECTION 07

# Recommended Next-Step Documents

This report is the strategic foundation. The documents below are the next layer — each should be owned by the function named in Section 05.

| Document | Owner | Priority |
| --- | --- | --- |
| Full Business Plan | Marketing & Finance | High |
| Marketing & Go-to-Market Strategy | Marketing | High |
| Financial Model & 12-Month Cash Flow | Finance & Advisory Ops | High |
| Client Service Level Agreement (SLA) templates | Legal & Compliance | High |
| HR Policy & First-Hire Job Descriptions | People & Learning | Medium |
| Data Privacy & Security Policy (for Data/Tech clients) | Technology & Legal | Medium |
| Academy Course Curriculum (first 2 courses) | People & Learning | Medium |
| RDB Activity-Code Review Memo | Legal & Compliance | High |

## Closing Note

Z-GATE LTD's registration already covers the legal and activity-code foundation for a four-division company — Advisory, Academy, Tech, and Data — plus one emerging fifth line in staffing/HR. The highest-leverage next step is narrowing focus: launch the 11 CORE activities under the brand system already built, hold the 5 ADJACENT activities for a 6–12 month review, and resolve the 5 REVIEW-status activities with legal counsel so the public registration record matches the business the market will actually see.